**03/22/20 – 03/28/20**

**Design**

* Comment resolution discussion with DCRA
* Address comments on permit application from DCRA
* Notification plan discussion with WMATA
* Resubmittal of Comment Matrix for Submittal D
* Resubmittal of Plans for Submittal D to DDOT and DC Water
* Obtain DC Water utility release letter
* Work on Permit applications for WMATA for Phase D

**Construction**

**Phase B**

* Trail Work - Excavate, install perforated underdrain and place stone at the proposed trail trench. . Asphalt paving at the proposed trail. Place stone for permeable pavers MBT 2.
* Electrical Work – Backfill electrical trench. Pull cables from MHs to the light poles.

**Phase D**

* Cut and remove trees.
* Clearing and grubbing

**03/29/20 – 04/04/20**

**Design**

* Comment resolution discussion with DCRA
* Address comments on permit application from DCRA
* Notification plan discussion with WMATA
* Resubmittal of Comment Matrix for Submittal D
* Resubmittal of Plans for Submittal D to DDOT and DC Water
* Obtain DC Water utility release letter
* Work on Permit applications for WMATA for Phase D

**Construction**

**Phase B**

* Trail Work – Switch pedestrian traffic to new trail, relocate Jersey Barrier. Excavate ditch along south side of the trail.
* Electrical Work – Excavate trench and install conduits from light poles to manhole. Install light pole foundations

**Phase D**

* Cut and remove trees
* Clearing and grubbing