**03/29/20 – 04/04/20**

**Design**

* Comment resolution discussion with DCRA
* Address comments on permit application from DCRA
* Notification plan discussion with WMATA
* Resubmittal of Comment Matrix for Submittal D
* Resubmittal of Plans for Submittal D to DDOT and DC Water
* Obtain DC Water utility release letter
* Work on Permit applications for WMATA for Phase D

**Construction**

**Phase B**

* Electrical Work – Pull cables from the manhole to the light poles. Form and concrete placement for light pole foundations. Installation of light poles along the proposed trail.
* Trail Work – Pervious pavers and Asphalt placement for the proposed trail. Ditch excavation along south side of the trail.

**Phase D**

* Cut and remove trees
* Clearing and grubbing
* CSX flagger’s operation and safety tool box talk

**04/05/20 – 04/11/20**

**Design**

* Comment resolution discussion with DCRA
* Address comments on permit application from DCRA
* Notification plan discussion with WMATA
* Resubmittal of Comment Matrix for Submittal D
* Resubmittal of Plans for Submittal D to DDOT and DC Water
* Obtain DC Water utility release letter
* Work on Permit applications for WMATA for Phase D

**Construction**

**Phase B**

* Electrical Work – Light pole foundations installation. Trench excavation and conduits installation from the light poles to the manhole.
* Trail Work – Divert pedestrian traffic to the proposed trail, relocate Jersey barriers. Ditch excavation along south side of the trail.

**Phase D**

* Cut and remove trees
* Clearing and grubbing
* CSX flagger’s operation and safety tool box talk