**04/05/20 – 04/11/20**

**Design**

* Comment resolution discussion with DCRA
* Address comments on permit application from DCRA
* Notification plan discussion with WMATA
* Resubmittal of Comment Matrix for Submittal D
* Resubmittal of Plans for Submittal D to DDOT and DC Water
* Obtain DC Water utility release letter
* Work on Permit applications for WMATA for Phase D

**Construction**

**Phase B**

* Electrical Work – Pull cables from the manhole to the light poles. Installation of light poles along the proposed trail.
* Trail Work – Asphalt paving for the proposed trail. Divert pedestrian traffic to the proposed trail, removal of Jersey barriers. Install silt fence. Ditch excavation along south side of the trail.

**Phase D**

* No work scheduled

**04/12/20 – 04/18/20**

**Design**

* Comment resolution discussion with DCRA
* Address comments on permit application from DCRA
* Notification plan discussion with WMATA
* Resubmittal of Comment Matrix for Submittal D
* Resubmittal of Plans for Submittal D to DDOT and DC Water
* Obtain DC Water utility release letter
* Work on Permit applications for WMATA for Phase D

**Construction**

**Phase B**

* Electrical Work – Electrical trench excavation, conduits installation, pull cables, Installation of light pole foundations and light poles installation.
* Trail Work – Ditch excavation along south side of the trail. Grading and place top soil and seeding. Install silt fence along the north side of the trail

**Phase D**

* Cut and remove trees
* Install silt fence
* Clearing and grubbing
* CSX flagger’s operation and safety tool box talk