**05/17/20 – 05/23/20**

**Design**

* Address WMATA and DDOT comments for railing Phase D
* Phase D 3-ring binder for 100% Plans

**Construction**

Phase B

* Electrical Work – Install temporary light poles foundation. Relocate solar panels poles on temporary foundation
* Trail Work - Ditch excavation and grading along the South side of the trail. Install soil stabilization matting at the swale along the South side of the trail.

Phase D

* Cut and remove trees
* Clearing and grubbing
* CSX flagger’s operation and safety tool box talk

**05/24/20 – 05/30/20**

**Design**

* Address WMATA and DDOT comments for railing Phase D
* Phase D 3-ring binder for 100% Plans

**Construction**

Phase B -

* Electrical Work – No work scheduled
* Trail Work – Ditch excavation and grading along the North side of the trail. Relocate pedestrians to the new trail. Removal of jersey barriers. Trail excavation at the connection area.

Phase D

* Cut and remove trees
* Clearing and grubbing
* CSX flagger’s operation and safety tool box talk