**05/24/20 – 05/30/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* WMATAs acceptance for Phase D Final Design Plans
* Phase D Emergency Action Plans
* Railing Design Submittal to WMATA and DDOT
* WMATA / DDOT Notification Plan for Phase D Construction Activities

**Construction**

Phase B

* Electrical Work – No work scheduled
* Trail Work – Backfill asphalt cores samples holes. Perform erosion control activities. Relocate pedestrians to the new trail.

Phase D

* Cut and remove trees
* Clearing and grubbing
* Perform grading
* Test pits
* Performing survey and marking
* Saw cut and demolish existing retaining wall
* Saw cut and demolish the existing parking lot pavement
* CSX flagger’s operation and safety tool box talk

**05/31/20 – 06/06/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* WMATAs acceptance for Phase D Final Design Plans
* Phase D Emergency Action Plans
* Railing Design Submittal to WMATA and DDOT
* WMATA / DDOT Notification Plan for Phase D Construction Activities

**Construction**

Phase B -

* Electrical Work – No work scheduled
* Trail Work – Ditch excavation and grading along the North side of the trail. Removal of jersey barriers. Trail excavation at the connection area of Phase B and Phase D.

Phase D

* Cut and remove trees
* Clearing and grubbing
* Perform grading
* Material delivery
* Saw cut and demolish the existing parking lot pavement
* CSX flagger’s operation and safety tool box talk