**06/07/20 – 06/13/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* Stakeholders Acceptance for Phase D Final Design Plans
* Railing Design Submittal to WMATA and DDOT
* NPS Approval for Phase D Emergency Action Plans
* WMATA / DDOT Notification Plan for Phase D Construction Activities
* DDOT Reviewed Means and Methods for Phase D construction activities
* WMATA Approval for SSWP Monitoring Plan
* CSX reviewing Phase D means and methods for construction activities

**Construction**

Phase B

* Electrical Work – Demolish existing light poles foundations. Install cable for pole to transformer pole.
* Trail Work – Perform Backfill and compaction at the demolished light poles foundations.

Phase D

* Clearing and grubbing
* Clear cut trees from site
* Saw cut and demolish existing retaining wall
* Saw cut and demolish the existing parking lot pavement
* Excavate retaining wall footings
* Perform grading
* Performing survey and marking
* Install silt fence
* Install safety fence
* Deliver storm pipes to site
* CSX flagger’s operation and safety tool box talk

**06/14/20 – 06/20/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* Railing Design Submittal to WMATA and DDOT
* CSX reviewing Phase D means and methods for construction activities

**Construction**

Phase B

* Electrical Work – No work scheduled
* Trail Work – No work scheduled

Phase D

* Cut and remove trees
* Clearing and grubbing
* Perform grading
* Install temporary pipe in the swale
* Install storm pipes end section
* Excavate retaining wall footings
* Perform survey and marking
* Deliver storm pipes to site
* Saw cut and demolish the existing parking lot pavement
* CSX flagger’s operation and safety tool box talk