**06/14/20 – 06/20/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* Stakeholders acceptance for Phase D Final Design Plans
* Railing Design Submittal to WMATA and DDOT
* WMATA / DDOT Notification Plan for Phase D Construction Activities
* Coordinate with CSX Approval of Phase D Means and Methods

**Construction**

Phase B

* Electrical Work – Demolish existing light poles foundations. Excavate, install conduits, back fill and compact electrical trench from manhole to manhole.
* Trail Work – Relocate pedestrian traffic to new trail. Remove Jersey Barriers. Ditch excavation and grading along the North side of the trail. Back fill and compact electrical trench.

Phase D

* Clearing and grubbing
* Clear cut trees from site
* Saw cut and demolish existing retaining wall
* Saw cut and demolish the existing parking lot pavement
* Excavate retaining wall footings
* Place Footing Rebars
* Install Silt and Safety Fence
* Install Temporary pipe in the swale
* Performing survey and marking
* Deliver storm pipes to site
* CSX flagger’s operation and safety tool box talk

**06/21/20 – 06/27/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* Stakeholders acceptance for Phase D Final Design Plans
* Railing Design Submittal to WMATA and DDOT
* Coordinate CSX Approval of Phase D Means and Methods

**Construction**

Phase B -

* Electrical Work – No work scheduled
* Trail Work – Ditch excavation and grading along the North side of the trail. Construction of Bio Swale along the North side of the trail.
* Phase D
* Install temporary pipe in the swale
* Install Storm Pipe End Section
* Excavate retaining wall footings
* Perform survey and marking
* Deliver storm pipes to site
* Install Storm Pipe End Section
* Saw cut and demolish the existing parking lot pavement
* CSX flagger’s operation and safety tool box talk