**06/21/20 – 06/27/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* Stakeholders acceptance for Phase D Final Design Plans
* Railing Design Submittal to WMATA and DDOT
* Coordinate with CSX Approval of Phase D Means and Methods

**Construction**

Phase B

* Electrical Work –Excavate, install conduits. Back fill and compact electrical trench
* Trail Work – Ditch excavation and grading along the North side of the trail. Construction of Bio Swale along the North side of the trail. Installation of 4” perforated pipe Bioswale pipe.

Phase D

* Install Silt and Safety Fence
* Perform grading
* Excavate retaining wall footings
* Install formwork for retaining wall footing
* Place retaining wall footing rebars
* Install temporary pipe in the swale
* Install pipes and manhole
* Performing survey and marking
* Deliver storm pipes to site
* CSX flagger’s operation and safety tool box talk

**06/28/20 – 07/04/20**

**Design**

* Phase D 3-ring binder for 100% Plans
* Stakeholders acceptance for Phase D Final Design Plans
* Railing Design Submittal to WMATA and DDOT
* Coordinate CSX Approval of Phase D Means and Methods

**Construction**

Phase B -

* Electrical Work – No work scheduled
* Trail Work – Ditch excavation and grading along the North side of the trail. Construction of Bio Swale along the North side of the trail. Installation of 4” perforated pipe Bioswale pipe.
* Phase D
* Excavate retaining wall footings
* Install formwork for retaining wall footing
* Place retaining wall footings concrete
* Install temporary pipe in the swale
* Install Storm Pipe End Section
* Excavate retaining wall footings
* Place retaining wall footings concrete
* Perform survey and marking
* Deliver storm pipes to site
* Install Storm Pipe End Section
* CSX flagger’s operation and safety tool box talk