Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

01/07/2021 – 02/13/2021

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- MBT Designer submitted Phase D 3-ring binder and 100% Plans to DDOT

- Stakeholders acceptance for Phase D Final Design Plans

- CSX is reviewing Phase D Means and Methods

Construction:

Phase B

- MPD Security Cameras  to be installed

- Glare Shields for Phase B trail lights to be installed

Phase D

- Excavated drainage trench

- Installed drainage pipes

- Constructed brick manhole

- Placed drainage pipes cradle concrete

- Installed retaining wall rebars

- Constructed retaining wall S2 wall section formwork

- Placed concrete for retaining wall S2 wall section

- Excavated electrical trench for manhole

- Installed electrical manhole

- Backfilled and compacted electrical manhole

- Backfilled and compacted electrical trench

- CSX flagger’s operation and safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were

Performed

- Reviewed PCCI Monthly Payment Invoice

- Reviewed Inspector Daily Reports

- Prepared CM Weekly Reports

- Attended DDOT CM PCCI Pending Change Orders and S3 Wall Modification  Discussion Meeting

- Updated Project Files

- Updated Project Webpage

- Updated documents in SharePoint

- Communication with the stakeholder in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Fri		02/12/21	MBT QAQC Meeting Conference Call was held at 10:00 A.M.

Fri	02/12/21	MBT DDOT DHA and PCCI Pending Change Orders and S3 Wall Modification discussion meeting was held at 2:00 P.M.

4.  DAILY WORK PERFORMED

Sun	02/07/21	No work performed.

Mon	02/08/21	Phase B – No work scheduled.

Phase B - Electrical Work – No work scheduled.

Phase D – Constructed retaining wall S2 formwork including ashlar pattern (column) and greenscreen panel.  Constructed brick manhole. Stripped drainage manholes cradle formwork.  Backfilled and compacted drainage trench. Backfilled and compacted drainage manholes.

Tue	02/09/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled

Phase D – Constructed retaining wall S2 formwork including ashlar pattern (column) and greenscreen panel.  Placed concrete for retaining wall S2 wall section. Constructed brick manhole. Backfilled and compacted drainage trench. Backfilled and compacted drainage manholes.

Phase D – Electrical Work – Excavated electrical manhole trench and placed bedding stone.  Installed electrical manhole.

Wed	02/10/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled.

Phase D – Constructed retaining wall S2 formwork including ashlar pattern (column) and greenscreen panel.  Placed concrete for retaining wall S2 wall section. Constructed brick manhole. Backfilled and compacted drainage trench. Backfilled and compacted drainage manholes.

Phase D – Electrical Work – Backfilled and compacted electrical manhole. Backfilled and compacted electrical trench.

Thurs	02/11/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled

Phase D – Work canceled due to rain.

Phase D – Electrical Work – Work canceled due to rain.

Fri	02/12/21	Phase B – No work performed.

Phase B – Electrical Work – No work scheduled

Phase D – Construct retaining wall S2 wall section formwork.  Constructed brick manhole. Excavated inlet trench. Installed drainage inlet.

Phase D – Electrical Work – No work performed.

Sat	02/13/21	No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test - Passed Asphalt Material Testing Concrete Material Testing – Pending results ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests Dynamic Cone Penetration (DCP) Tests - Passed Rebars Inspection - Passed |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 46% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 58% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase B – No work performed

Phase B – No work performed

Phase D – Crew installing retaining wall S2 rebars

Phase D – Crew constructing retaining wall S2 formwork

Phase D – Crew compacting drainage trench

Phase D – Crew placing concrete for retaining wall S2 wall section

Phase D – Crew placing concrete for retaining wall S2 wall section

Phase D – Electrical crew installing electrical manhole

Phase D – Crew constructing retaining wall S2 formwork

Phase D – Crew constructing drainage manhole

Phase D – Crew constructing retaining wall formwork

Phase D – Crew compacting electrical manhole