Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

02/28/2021 – 03/06/2021

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- MBT Designer submitted Phase D 3-ring binder and 100% Plans to DDOT

- Stakeholders acceptance for Phase D Final Design Plans

Construction:

Phase B

- MPD Security Cameras  to be installed

- Glare Shields for Phase B trail lights to be installed

Phase D

- Constructed brick manhole inverts

- Constructed retaining wall S2 formwork

- Shaft drilled electrical poles foundations

- Installed pre-assembled rebars in electrical manhole

- Installed electrical conduits for the proposed cameras

- Delivered precast inlets

- CSX flagger’s operation and safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were

Performed

- Reviewed PCCI Monthly Payment Invoice

- Preparing Contract Modification package

- Reviewed Inspector Daily Reports

- Prepared CM Weekly Reports

- Attended MBT Progress Meeting

- Attended DDOT PCCI DHA and Designer Meeting

- Updated Project Files

- Updated Project Webpage

- Updated documents in SharePoint

- Communication with the stakeholder in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Tue	03/02/21	MBT Progress Meeting conference call was held at 10:00 A.M.

Wed	03/03/21	MBT DDOT DHA PCCI and Designer Project Coordination Meeting conference call meeting was held at 9:00 A.M.

Fri	03/05/21	QAQC Meeting conference call was held at 10:00 A.M.

4.  DAILY WORK PERFORMED

Sun	02/28/21	No work performed.

Mon	03/01/21	Phase B – No work scheduled.

Phase B - Electrical Work – No work scheduled.

Phase D – No work performed due to rain.

Phase D – Electrical Work – No work performed due to rain.

Tue	03/02/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled.

Phase D – Constructed retaining wall S2 formwork.  Constructed brick manhole. Repaired silt fence.

Phase D – Electrical Work – Shaft drilled electrical foundations. Installed pre-assembled rebars. Installed light pole foundation formwork. Installed light pole foundation conduits.

Wed	03/03/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled.

Phase D – Constructed retaining wall S2 formwork. Placed concrete for retaining wall S2 wall section.  Constructed brick manholes. Delivered precast inlets.

Phase D – Electrical Work – Shaft drilled electrical foundations. Installed pre-assembled rebars. Installed light pole foundation formwork. Installed light pole foundation conduits.

Thurs	03/04/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled

Phase D – Constructed retaining wall S2 formwork. Placed concrete for retaining wall S2 wall section.  Constructed brick manholes. Backfilled and compacted drainage trench. Repaired silt fence.

Phase D – Electrical Work – Shaft drilled electrical foundations. Installed pre-assembled rebars. Installed light pole foundation formwork. Installed light pole foundation conduits.

Fri	03/05/21	Phase B – No work scheduled.

Phase B – Electrical Work – No work scheduled

Phase D – Constructed retaining wall S2 formwork. Placed concrete for retaining wall S2 wall section.  Constructed brick manholes. Backfilled and compacted drainage trench.  Repaired sit fence.

Phase D – Electrical Work – Shaft drilled electrical foundations. Installed pre-assembled rebars. Installed light pole foundation formwork. Installed light pole foundation conduits. Placed concrete for light poles foundation.

Sat	03/06/21	No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test - Passed Asphalt Material Testing Concrete Material Testing – Pending results ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests Dynamic Cone Penetration (DCP) Tests - Passed Rebars Inspection - Ongoing |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 46% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 58% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase D – No work performed

Phase B- No work performed

Phase D – Crew constructing manhole

Phase D – Crew shaft drilling light pole foundation

Phase D – Crew setting Lightpole foundation formwork

Phase D – Crew constructing retaining wall formwork

Phase D – Crew placing retaining wall concrete

Phase D – Crew constructing retaining wall S2 formwork

Phase D – Crew compacting drainage trench

Phase D – Crew placing concrete for light pole foundation