Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

05/31/2020 – 06/06/2020

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- Phase D 3-ring binder for 100% Plans

- Stakeholders Acceptance for Phase D Final Design Plans

- Railing Design Submittal to WMATA and DDOT

- NPS Approval for Phase D Emergency Action Plans

- WMATA / DDOT Notification Plan for Phase D Construction Activities

- DDOT Reviewed Means and Methods for Phase D construction activities

- WMATA  Approval for SSWP Monitoring Plan

- CSX reviewing Phase D means and methods for construction activities

Construction:

Phase B

- Watered the seeded area

- Installed silt fence along the North side of the fence

- Install safety fence along the North side of the fence

- Pepco onsite to take measurements for the relocation of Pepco transformer

Phase D

- Cut trees and cleared the cut trees from the job site

- Installed silt fence along the existing sidewalk

- Performed rough grading

- Sawcut and demolished existing concrete slab.

- Performed surveying and marking storm pipe stakeout

- Excavated test pits

- Delivered storm pipes to the site.

CM Consultant:

- Monitored construction progress, make sure all applicable inspection and testing were performed

- Reviewed Inspection Daily Reports

- Reviewing Invoice for May.

- Updated Project Files

- Updating documents in SharePoint

- Communication with the stakeholder in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Tue.	06/03/20	DDOT PEPCO PCCI field meeting was held at 8:30 A.M.

Thur.	06/04/20	DDOT QA Meeting conference call was held at 11:00 A.M.

Fri.	06/05/20	QA/QC Meeting conference call was held at 10:00 A.M.

Fri.	06/05/20            DDOT CSX Coordination Meeting was held at 8:00 A.M.

4.  DAILY WORK PERFORMED

Sun	05/31/20	No work performed

Mon	06/01/20	Phase B – installed the silt fence along the north side of the trail.

Installed safety fence along the north side of the trail.  Delivered five temporary light poles bases to the site.

Phase D - Cut and cleared the cut trees from the site.

Tue	06/02/20	Phase 	B – Watered the landscape.  Pepco electricians were onsite to

take measurements and to coordinate the upcoming installation of the

secondary transformer.

Phase B - Electrical Work – No work performed.

Phase D - Cleared the cut trees from the site. Performed rough grading.  Installed silt fence.  Surveyor performed survey and marking stormwater pipes stakeout.  Excavated test pits.

Wed	06/03/20	Phase B - No work performed

Phase B - Electrical Work – No work performed

Phase D - Excavated test pits.  Sawcut the existing concrete slab.  Installed silt fence. Cleared the cut trees from the site.

Thurs	06/04/20	Phase B - No work performed

Phase B - Electrical Work – Removed light pole foundation. Excavated and compacted electrical conduit trench.  Relocated six solar light poles on temporary lightpole bases.

Phase D – Installed silt fence. Sawcut the existing concrete slab. Demolished the existing concrete slab.

Fri	06/05/20	Phase B – No work performed.

Phase B - Electrical Work – No work performed.

Phase D – Cleared cut trees from the site. Demolished the existing concrete slab.

Sat	06/06/20	No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test Asphalt Material Testing Concrete Material Testing | Infiltration facility Material Testing |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 36% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 0% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase B – Crew installing safety fence along the North side of the trail

Phase B – Crew watering the landscape

Phase B – Crew attending daily safety briefing

Phase B – Crew compacting trench

Phase D – Crew cutting the tree

Phase D – Crew unloading drainage pipes

Phase D – Crew installing silt fence

Phase D – Crew clearing cut trees

Phase D – Crew saw cutting the existing concrete slab

Phase D – Crew excavating to install silt fence

Phase D – Crew demolishing existing concrete

Phase D – Crew attending safety briefing