Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

07/04/2021 – 07/10/2021

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- 100 % Complete

Construction:

Phase D

- Performed excavation and grading for trail

- Installed geotextile fabric at trail subgrade

- Installed 4” perforated underdrain pipe

- Placed and graded trail bedding stone

- Constructed retaining wall S0 footing formwork

- Installed retaining wall S0 footing rebar

- Placed retaining wall S0 footing concrete

- Constructed retaining wall S0 wall section formwork

- Installed retaining wall S0 wall section rebar

- Shaft-drilled retaining wall S3 foundation

- Assembled retaining wall S3 shaft foundation rebar cage

- Installed retaining wall S3 H piles

- Placed concrete for retaining wall S3 foundation

- Excavated chain link fence footing

- Placed concrete for fence post footing

- Pulled conductors for trail light poles

- CSX flagger’s operation and safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were performed

- Reviewed PCCI monthly invoice

- Reviewed CSX Invoice

- Prepared Change Order package

- Prepared CM Weekly Report to post

- Prepared CM weekly report to DDOT

- Attended MBT Project  Progress Meeting

- Attended on site meeting with Aggregate Industries

- Monitored QC field testing

- Updated Project Files

- Updated Project Logs

- Updated Project Webpage

- Updated documents in DHA SharePoint site

- Updated DDOT Sharepoint site

- Communication with PCCI and stakeholders in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Tue	07/06/2021	MBT Progress Meeting conference call was held at 10:00 A.M.

Fri	07/09/2021	DHA and Aggregate Industries site meeting was held at 10:30 A.M.

4.  DAILY WORK PERFORMED

Sun	07/04/21	No work performed.

Mon	07/05/21	Phase D – Independence Day Holiday.

Tue	07/06/21	Phase D – Placed concrete for retaining wall S0 footing. Shaft-drilled retaining wall S3 foundation.  Installed rebar cage and H piles for S3 wall foundation. Placed concrete for S3 foundations.  Excavated fence post footing. Installed sonotube for fence post footing.  Placed concrete for fence post footing.

Phase D – Electrical Work – Pulled conductors for light poles.

Wed	07/07/21	Phase D – Constructed retaining wall S0 wall section formwork. Installed S0 wall section rebar.  Shaft-drilled retaining wall S3 foundation.  Installed rebar cage and H piles for S3 wall foundation. Placed concrete for S3 foundations.  Excavated trail path. Placed and graded stone at trail path.

Phase D – Electrical Work – Pulled conductors for light poles. Installed trail light poles. Pulled dragline for electrical conduits installed.

Thurs	07/08/21	Phase D – Wet cured retaining wall S0 footing concrete. Constructed retaining wall S0 wall section formwork. Installed retaining wall S0 wall section rebar. Assembled and installed H piles cage. Placed concrete for retaining wall S3 foundation.  Placed concrete for S3 foundations. Installed geotextile fabric. Installed 4” perforated trail underdrain. Placed and graded bedding stone at the trail.

Phase D – Electrical Work – On site performed general clean up.

Fri	07/09/21	Phase D – Constructed retaining wall S0 wall section formwork. Installed

retaining wall S0 wall section rebar. Assembled and installed H piles and rebar cage. Placed concrete for retaining wall S3 foundation.  Placed and graded bedding stone at the trail.

Phase D – Electrical Work – No work performed.

Sat	07/10/21		Phase D – No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test Asphalt Material Testing Concrete Material Testing – Pending results ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests Dynamic Cone Penetration (DCP) Tests Rebars Inspection - Passed |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 49.4% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 82.7% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase D – Crew placing concrete for retaining wall S0 footing

Phase D – Crew excvating trail path

Phase D – Crew pulling light pole wires

Phase D – Crew placing fence post concrete

Phase D – Crew shaft-drilling retaining wall S3 foundation

Phase D – Crew placing concrete retaining wall S3 foundation concrete

Phase D – Crew insatlling the trail geotextile

Phase D – Crew grading the trail stone

Phase D – Crew wet cuing retaining wall S0 footing concrete

Phase D – Crew constructing retaining wall S0 wall section formwork

Phase D – Crew insatlling retaining wall S3 drilled shaft cage and H pile

Phase D – Crew tying retaining wall S3 founation rebar cage