Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

08/15/2021 – 08/21/2021

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- 100 % Complete

Construction:

Phase D

- Constructed retaining wall S0 wall section formwork

- Performed excavation in front of retaining wall S3

- Constructed retaining wall S3 footing formwork

- Installed retaining wall S3 footing rebar

- Dewatered retaining wall S3 footing

- Excavated and graded the trail path

- Installed geotextile fabric at the trail subgrade

- Installed 4” underdrain at the trail path

- Placed and graded bedding stone at the trail

- Compacted the trail bedding stone

- Installed cap on the trail clean outs

- Insatlled cable racks in electrical manholes

- Installed ground rods in electrical manhole

- Contractor safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were performed

- Attended MBT Progress Meeting

- Attended MBT Project Field Meeting with PCCI

- Prepared CM Weekly Report to post

- Prepared CM weekly report to DDOT

- Monitored QC field testing

- Updated Project Files

- Updated Project Logs

- Updated Project Webpage

- Updated documents in DHA SharePoint site

- Updated DDOT Sharepoint site

- Communication with PCCI and stakeholders in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Tue	08/17/21	MBT Progress Meeting conference call was held at 10:00 A.M.

Wed	08/18/21	Site Meeting was held between DHA and PCCI at 9:30 A.M.

4.  DAILY WORK PERFORMED

Sun	08/15/21	No work performed.

Mon	08/16/21	Phase D – Constructed retaining wall S0 formwork. Installed retaining wall

S0 wedge wall rebars.  Excavated the trail path. Installed geotextile at the

trail.  Installed 4” perforated underdrain pipe. Placed and graded bedding stone at the trail.  Performed excavation in front of retaining wall S3 for bedding pad. Placed and graded bedding stone for retaining wall S3 footing.

Phase D – Electrical Work – No work performed.

Tue	08/17/21	Phase D – Constructed retaining wall S0 formwork.  Performed excavation 		in front of retaining wall S3 for bedding pad. Constructed retaining wall S3

footing formwork. Excavated the trail path. Installed geotextile fabric at the

trail. Installed 4” perforated underdrain pipe. Placed and graded bedding

stone at the trail path.

Phase D – Electrical Work – No work performed.

Wed	08/18/21	Phase D – Constructed retaining wall S0 wall section formwork. Constructed

retaining wall S3 footing formwork.  Installed retaining wall S3 footing rebars.  Excavated the trail path. Installed geotextile fabric at the trail.  Installed 4” perforated underdrain pipe. Placed and graded bedding stone at the trail.

Phase D – Electrical Work – No work performed.

Thurs	08/19/21	Phase D – Constructed retaining wall S0 wall formwork.  Graded and compacted bedding stone.  Constructed retaining wall S3 footing formwork.  installed retaining wall S3 footing rebars. Performed excavation in front of retaining wall S3.

Phase D – Electrical Work – Installed racks in electrical manholes.  Installed ground rods in electrical manholes.

Fri	08/20/21	Phase D – Work canceled due to rain.

Phase D – Electrical Work – No work performed due to rain.

Sat	08/21/21		Phase D – No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test Asphalt Material Testing Concrete Material Testing – Pending results ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests Dynamic Cone Penetration (DCP) Tests Rebars Inspection – Ongoing |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 54.4% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 96.6% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase D – Crew grading the trail stone

Phase D – Crew excavating the trail path

Phase D – Crew constructing retaining wall S0 formwork

Phase D – Crew installing cable racks in electrical manhole

Phase D – Crew installing retaining wall S3 rebars

Phase D – Crew excavating for retaining wall S bedding pad

Phase D – Crew compacting the trail bedding stone

Phase D – Crew installing cleanout cap