Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

08/22/2021 – 08/28/2021

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- 100 % Complete

Construction:

Phase D

- Constructed retaining wall S0 wall section formwork

- Placed concrete for retaining wall S0 wall section

- Removed formwork of RW S0 wall section

- Constructed retaining wall S3 footing formwork

- Installed retaining wall S3 footing rebar

- Dewatered retaining wall S3 footing

- Placed concrete for retaining wall S3 footing

- Excavated south side curb

- Placed concrete for south side curb

- Placed and graded bedding stone at the trail

- Installed inlet clean out pipes

- Installed cable racks in electrical manholes

- Installed ground rods electrical manholes

- Pulled conductors for trail light poles

- Contractor safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were performed

- Reviewed CSX invoice

- Attended MBT Project Field Meeting with PCCI

- Prepared CM Weekly Report to post

- Prepared CM weekly report to DDOT

- Monitored QC field testing

- Updated Project Files

- Updated Project Logs

- Updated Project Webpage

- Updated documents in DHA SharePoint site

- Updated DDOT Sharepoint site

- Communication with PCCI and stakeholders in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Thur	08/26/21	DHA DDOT and PCCI on site meeting was held at 8:30 A.M.

4.  DAILY WORK PERFORMED

Sun	08/22/21	No work performed.

Mon	08/23/21	Phase D – Constructed retaining wall S0 wall section formwork. Installed

retaining wall S0 wedge wall rebars. Removed retaining wall S0 wall section

rebar. Dewatered and cleaned retaining wall S0 footing.  Excavated south side curb.

Phase D – Electrical Work – Installed cable racks in manhole. Installed manhole ground rods.

Tue	08/24/21	Phase D – Constructed retaining wall S0 formwork.  Constructed retaining

wall S3. Dewatered and cleaned retaining wall S3 footing. Constructed

retaining wall S3 footing formwork.  Installed retaining wall S3 footing rebar.

footing formwork. Constructed formwork for south side curb.  Placed concrete for south side curb.

Phase D – Electrical Work – Pulled conductors for trail light poles.

Wed	08/25/21	Phase D – Placed concrete for retaining wall S0 concrete. Dewatered

retaining wall S3 footing. Constructed retaining wall footing formwork.

Installed retaining wall footing rebar.  Removed south side curb formwork.

Phase D – Electrical Work – Pulled conductors for trail light poles.

Thurs	08/26/21	Phase D – Wet cured retaining wall S0 wall concrete. Dewater retaining wall S3 footing.  Cleaned retaining wall S3 footing rebars and formwork.  Placed concrete for retaining wall S3 footing. Excavated and graded sloped area behind retaining wall S3. Graded trail bedding stone.  Installed cleanout pipes at the trail.

Phase D – Electrical Work – Pulled conductors for trail light poles

Fri	08/27/21	Phase D – Wet cured retaining wall S0 concrete.  Dewatered retaining wall S3 footing.  Repaired silt fence.  Performed general cleanup site wide..

Phase D – Electrical Work – Pulled conductors for trail light poles.

Sat	08/28/21		Phase D – No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test Asphalt Material Testing Concrete Material Testing – Pending results ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests Dynamic Cone Penetration (DCP) Tests Rebars Inspection – Passed |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 54.4% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 96.6% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase D – Crew installing cable rack in electrical manhole

Phase D – Crew installing rebar at retaining wall S3

Phase D – Crew constructing south side curb formwork

Phase D – Crew constructing retaining wall S0 formwork

Phase D – Crew placing concrete for north side curb

Phase D – Crew placing retaining wall S0 concrete

Phase D – Crew pressure washing retaining wall S3 footing rebar

Phase D – Crew excavating embankment area behind retaining wall S3

Phase D – Crew grading bedding stone at the trail

Phase D – Crew installing clean out pipe

Phase D – Crew pulling conductor for trail light pole

Phase D – Crew placing concrete for retaining wall S3 footing