Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

10/18/2020 – 10/24/2020

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- MBT Designer submitted Phase D 3-ring binder and 100% Plans to DDOT

- Stakeholders acceptance for Phase D Final Design Plans

- CSX is reviewing Phase D Means and Methods

- Redesign of Retaining Wall S2 under review

Construction:

Phase B

- Delivered Bioswale trees

- Constructed bioretention pond

- Placed topsoil around the island area

- Adjusted drainage manhole

- Excavated tree pits

Phase D

- Stripped retaining wall formwork

- Performed backfilling and compaction behind retaining wall

- Excavated drainage trench

- Installed and backfilled drainage pipes

- Constructed manholes

- CSX flagger’s operation and safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were

Performed

- Attended QAQC Meeting conference call

- Attended DDOT DHA meeting conference call

- Reviewed Inspection Daily Reports

- Prepared CM Weekly Reports

- Updated Project Files

- Update Project Webpage

- Updated documents in SharePoint

- Communication with the stakeholder in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

Wed	10/21/20	DDOT DHA coordination meeting was held at 9:00 A.M.

Fri	10/23/20	QAQC Meeting conference call was held at 10:00 A.M.

4.  DAILY WORK PERFORMED

Sun	10/18/20	No work performed.

Mon	10/19/20	Phase B – Excavated and hauled materials from triangle area. Delivered

Bioswale plants. Adjusted drainage manhole.

Phase B – Electrical Work – No work scheduled.

Phase D - Placed retaining wall concrete.  Performed backfilling and compaction behind retaining wall. Installed drainage pipes. Backfilled drainage trench. Constructed drainage manhole.

Tue	10/20/20	Phase B – Excavated and hauled materials from triangle area. Placed

planting soil around the island area.

Phase B – Electrical Work – No work scheduled

Phase D – Performed rough grading along the trail. Stripped retaining wall wedge forms. Performed backfilling and compaction behind retaining wall.  Placed porous backfill behind retaining wall. Installed drainage pipes. Backfilled drainage trench. Constructed drainage manhole.

Wed	10/21/20	Phase B – Excavated bioretention pond. Placed topsoil at the island

area. Hauled away excavated materials from the site.  Cleaned site.

Phase B - Electrical Work – No work scheduled.

Phase D – Demolished and removed existing concrete ditch.  Perform rough grading.  Performed backfilling and compaction behind retaining wall.  Placed porous backfill behind retaining wall. Installed drainage pipes. Backfilled drainage trench. Constructed drainage manhole.

Thurs	10/22/20	Phase B – Excavated Bioretention pond and hauled away excavated

materials.  Excavated tree pits.

Phase B – Electrical – No work scheduled

Phase D – Demolished and removed existing concrete ditch.  Perform rough grading. Backfilled and compacted trail embankment. Stripped retaining wall formwork. Performed backfilling and compaction behind retaining wall.  Placed porous backfill behind retaining wall. Installed drainage pipes. Backfilled drainage trench. Constructed drainage manhole. Installed manhole base slab rebars.

Fri	10/23/20	Phase B – Excavated Bioretention pond and hauled away excavated

materials.  Excavated tree pits.

Phase D – Perform rough grading.  Backfilled and compacted trail embankment.  Performed backfilling and compaction behind retaining wall. Installed drainage pipes. Backfilled drainage trench. Placed manhole base concrete.

Sat	10/24/20	No work scheduled

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test - Passed Asphalt Material Testing Concrete Material Testing – Pending results ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests – Pending results Dynamic Cone Penetration (DCP) Tests Rebars Inspection - Passed |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 40% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 18% of their Goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase B – Crew adjusting manhole

Phase B – Crew placing planting soil in Island area

Phase B – Crew excavating Bioretention pond area

Phase B – Crew excavating for the tree pits

Phase D – Crew placing retaining wall concrete

Phase D – Crew compacting backfill behind retaining wall

Phase D – Crew performing trail grading

Phase D – Crew placing porous backfill behind retaining wall

Phase D – Crew placing fill at the trail

Phase D – Crew stripping retaining wall formwork

Phase D – Crew installing manhole base rebars

Phase D – Crew installing drainage pipes