Metropolitan Branch Trail Design Build, South Segment

DC CONTRACT NO. DCKA-2016-C-0044

FAP No.: STP-2016 (060)

CONSTRUCTION MANAGER’S

WEEKLY PROGRESS REPORT

11/21/2021 – 11/27/2021

Project Website: www.metbranchtrail-forttotten.com

For Additional Trail Information Please see www.metbranchtrail.com

Proposed Metropolitan Branch Trail

1.  PROJECT DESCRIPTION

The planned Metropolitan Branch Trail Project (“the Project”) consists of the design and construction of a new trail adjacent to CSX tracks and WMATA Red Line tracks along John McCormack Drive, adjacent to Fort Totten Metro Station, and on NPS property in NE, Washington D.C.  The trail begins approximately 1500 feet south of Bates Road NE on the east side of John McCormack Drive NE, extending north along the WMATA and CSX tracks to the Fort Totten Metro Station tie in with First Place NE.  An existing trail connection from Gallatin Road NE to the Fort Totten Metro Station will be reconstructed as a part of the Project.

The Project is 83.15% Federally-Funded and 16.85% District-Funded. Potomac Construction is the Design Build contractor.

Delon Hampton and Associates Chartered is providing Construction Management and Inspection services.   Specific Construction Scope of Work includes:

- Provide mobilization and demobilization, provision and maintenance of Engineer’s field facilities, field layout, employee training, and other incidental work required for a quality, complete and finished product;

- Establishment and maintenance of vehicular and pedestrian traffic including signs, barricades and other transition devices; reconfiguring the devices in conjunction with changes in work areas; and their removal and disposal upon project completion, including restoration of disturbed areas;

- Clearing and grubbing, as required within the LOD;

- Removal of unsuitable material, excavation, and backfilling and pervious paving to construct a new trail;

- Protection of trees during construction;

- Provide ADA compliant trail connections and pedestrian ramps;

- Provide retaining walls as necessary to stay within the LOD and minimize property impacts following visual requirements specified for retaining walls on NPS property;

- Provide new permanent regulatory and wayfinding signs for the trail and all trail connection intersections;

- Provide road and trail pavement markings;

- Provide landscaping within the LOD for the Project including special requirements for landscaping on NPS property;

- Provide erosion and sediment control measures, storm water management facilities, including pervious asphalt pavement and bioretention facilities;

- Provide utility coordination, identification, locating, and protection of all utilities encountered during design and construction including relocation of Pepco poles along Aggregate Industries property; and

- Provide new WMATA security fencing between the trail and CSXT tracks.

- Remove existing sidewalk and widen sidewalk to 10’ along the west side of 1st place NE from Metropolitan Branch Trail to entrance to WMATA bus loop, on the west side.

2.  STATUS OF CONSTRUCTION / PROGRESS SUMMARY

Work performed this week:

Design

- 100 % Complete

Construction:

Phase D

- Performed excavation for drainage manhole

- Installed drainage manhole bottom mat rebar

- Constructed formwork for drainage manhole

- Performed excavation for precast drainage inlet

- Installed precast drainage inlet

- Performed excavation for WMATA stairs

- Constructed formwork for WMATA stairs

- Painted S3 wall panels and ashlar pattern pilasters

- Parged S3 wall front and back face

- Excavated test pit for installation of drainage pipes

- Contractor safety tool box talk

CM Consultant:

- Monitored construction progress, make sure all applicable inspections and testing were performed

- Reviewed Project Schedule

- Reviewed Monthly payment invoice

- Prepared CM Weekly Report to post

- Prepared CM weekly report to DDOT

- Updated Project Files

- Updated Project Logs

- Updated Project Webpage

- Updated documents in DHA SharePoint site

- Updated DDOT Sharepoint site

- Communication with PCCI and stakeholders in terms of submittals

3.  MEETINGS / PROJECT COORDINATION

11/23/2021	MBT progress meeting was held at 10.00 A.M.

4.  DAILY WORK PERFORMED

Sun	11/21/21	No work performed.

Mon  	11/22/21	Phase D – Performed excavation for WMATA stairs.  Constructed formwork

for WMATA stairs.  Performed excavation for drainage manhole. Assembled

rebar for manhole base. Excavated test pit for fiber optic lines near

drainage manhole.  Painted S3 wall panels and pilasters.

Phase D – Electrical work – No work performed.

Tue  	11/23/21	Phase D – Constructed formwork for WMATA stairs.  Installed rebar for

drainage manhole base. Performed excavation for recast drainage inlet.

Painted S3 wall panels and pilasters. Cleaned S3 wall footing area. Parged front and back face of S3 wall.

Phase D – Electrical work – No work performed.

Wed       11/24/21 	Phase D – Constructed formwork for WMATA stairs.

Performed excavation for recast drainage inlet. Installed precast drainage inlet.  Painted S3 wall panels and pilasters. Cleaned S3 wall footing. Parged front and back face of S3 wall.

Phase D – Electrical work – No work performed.

Thurs   	11/25/21	Phase D – No work performed.  Thanksgiving Holiday

Phase D – Electrical Work – No work performed.

Fri	11/26/21	Phase D – No work performed.  Thanksgiving Holiday

Phase D – Electrical Work – No work performed.

Sat	11/27/21		Phase D – No work scheduled.

5.  INSPECTION & MATERIAL TESTS PERFORMED

| Jobsite Safety Inspection Erosion and Sediment Control inspection MOT Inspection Compaction Test Asphalt Material Testing Concrete Material Testing ** Note - Additional Material Test Results can be found on DDOT QA QC Material Division Tracking SharePoint website. | Infiltration Tests Dynamic Cone Penetration (DCP) Tests Rebars Inspection – Ongoing |
| --- | --- |

6.  DBE PARTICIPATION SUMMARIES

Potomac Construction Inc. (Contractor)

- DBE Goal for Contractor is 15%.  To-date the Contractor has achieved 55% of their goal.

Delon Hampton & Associates (CM)

- DBE Goal for the CM is 10%. To-date the CM has achieved 97% of their goal.

7.  ACCIDENTS / INCIDENTS

None occurred on-site during this week.

8. PHOTOS OF THE WORK PERFORMED

12.  PHOTOS OF WORK PERFORMED THIS PERIOD

Phase D – Crew performing test pit

Phase D – Crew constructing formwork for WMATA stairs

Phase D – Crew cleaning in front of S3 wall

Phase D – Crew parging S3 wall front face

Phase D – Crew parging back side of S3 wall

Phase D – Crew painting S3 wall pilasters

Phase D – Crew installing precast drainage inlet

Phase D – Crew installing inlet top

Phase D – Drainage manhole bottom mat rebar installed

Phase D – Crew cleaning S3 wall footing

Phase D – Retaining wall S3 panels and pilasters painted